## Slide 1: Review of Universal Credit
Veronica Marshall
18 February 2016

## Slide 2: Structure of today’s talk
Background and context
The Universal Credit Programme
What went wrong?
UC: Where are we now?
Questions?
Data and figures are taken from the NAO report “Universal Credit: Early Progress”, Sep 2013 and NAO report “Universal Credit: Update” Oct 2014 unless otherwise stated.

## Slide 3: Background and Context

## Slide 4: Economic context
When the coalition came to power in May 2010, the UK was suffering the worst economic recession for 60 years.
  Decrease in Gross Domestic Product between early 2008 and early 2010
5%
  In 2009/10 Government spending was nearly 50% of GDP.
50%
£141bn
  2010/11 net borrowing, 7.6% of GDP.
  Total spend by government in 2010/11
£692bn

## Slide 5: The drive to reduce public spending
In June 2010, George Osborne announced the deepest cuts ever seen in the public sector by ordering nearly all government departments to slash an average of 25% from their annual budgets before the next general election.
£11bn
From the welfare budget
Cancelled capital projects
£2bn
£3bn
On debt interest
From departmental budgets
£61bn
Data source: Cabinet Office Statistics 2013

## Slide 6: 2014 UK Economy: Continued Pressure on Public Finance
2014: Budget deficit reduced by £6.3 billion to £91.3 billion, half the expected reduction.
2014: Wage and productivity growth disappointing leading to decreased tax revenues.
2014: Government spending pushed borrowing in Sep 2014 to £11.8bn, £1.6bn higher than September 2013.
2015-16: Net debt is forecast to rise by 0.8 per cent of GDP

## Slide 7: The Universal Credit Programme

## Slide 8: Department of Work and Pensions
£12.57bn
£8.11bn
£5.45bn
Disability living
allowance
Pension credit
Rent rebates
Statutory sick and maternity pay
Social Fund
Incapacity benefit
Council
tax benefit
Job seeker’s allowance
Employment & support allowance
£4.83
bn
£4.91
bn
£2.55bn
£2.37 bn
£1.73 bn
£4.94
bn
Housing benefit £16.94bn
State pensions
£74.22bn
£167 billion
Department for Work & Pensions (DWP) was the biggest spending department in the UK.
23%
Of all public spending is spent on benefits
Total departmental spending
£166.98bn
2011/12
Spending Analysis 2011/12
Data source: Guardian analysis of public sector spending, 2011-12
£5.34
bn
Attendance allowance
£3.58bn
Carers allowance
£1.73 bn
Financial assistance scheme
State benefits
spending
£159bn

## Slide 9: What is Universal Credit?
Business Case
December 2012
Benefits to be achieved:
Universal Credit
Job
Seekers Allowance
Working Tax Credit
Housing Benefit
Child Tax Credit
Employment Support
Allowance
Income Support
Universal Credit is a new benefit that will replace 6 existing benefits with a single monthly payment.
The design of UC assumes the new service will be digital by default with 80% of claimants making claims and administering changes of circumstance on line.
£7 billion
£38 billion
8.2 million
DWP estimate of net benefit from 2010/11 – 2022/23
DWP estimate of annual net benefit from 2022/23
DWP estimate of UC claimants by 2017

## Slide 10: Universal Credit aims
New
claims
Claimant
culture
Claimant
obligations
Work
support
Incentives
Changes in
earnings
Other changes
Claimant journey
Simplify benefits and reduce
confusion
Reduce the need to make new
claims when circumstances change
Encourage responsibility for
managing household budgets
Reduce welfare dependency
Increase job search skills and
preparation for work
Tie support more clearly to
conditions and incentives
Improve and make clearer the
incentives to work
Remove burden of closing and
reopening claims when moving
into work or reporting changes in
earned income
Simplify and improve reporting of
changes in circumstances
Consolidates six working-age benefits
into one
Aims for 80 per cent of claims
made online
Makes a single monthly payment
directly to claimant (rather than,
for example, the landlord)
Increases job search through
‘claimant commitment’
Extends work search conditions to
claimants in work
Clarifies how sanction regime relates
to conditions
Links to record of search on new
Universal Jobmatch system
Limits benefits withdrawal rate to
65 per cent of increase in income
Increases some disregards
Clarifies ‘better off’ calculations
Updates earnings automatically using
real time information (RTI)
Claimants update self-employed
income themselves online
Claimants report changes in
circumstances online
Claimants report childcare costs online
Aims
Changes

## Slide 11: Programme costs

## Slide 12: A complex landscape of stakeholders
Local authorities
Citizen’s advice Bureau
Housing associations
Private
Landlords
Charities
DWP
CESG
GDS
UC
MPA
Social services
Job Advisors
HMT
Banks
Credit agencies
HMRC
Claimants
IBM
Detica
HP
Accenture
BT
Francis Maude
Ian Duncan Smith
Robert Devereux
Howard Shiplee

## Slide 13: Core components of Universal Credit
Policy clarity
Requirements clarity
Leadership
Vision
Commitment
Culture
Communications
Stakeholder engagement
Ensuring stakeholder support
Clear delivery plans
Risk management
Programme
assurance
management
& control
Procurement
Financial management
Universal Credit
Claimant journey
Access to systems (digital by default)
Migration plans
Staff training
Management information
Premises alterations
IT infrastructure
Identity assurance
Secure
processes
Systems integration
Legacy systems

## Slide 14: Universal Credit IT systems components
Financial and payments systems
Security systems
Management Information systems
Claims administration
systems
Security operations centre
Document processing & case load management
Claimant interface
Internet
Interface
Identity assurance
Cyber
security
Fraud and error
Work
services module
Business process management
Evidence system
RTI
Customer account management
Interview
system
Evidence
system
Rules engine
Real time earnings
Payments calculation
Payment management system
Claim system
Bank wizard
Address verification
Claimant identification systems
Real time information system
Provider referral system
Customer information system

## Slide 15: An ambitious rollout timetable

## Slide 16: Which methodology to use?
Waterfall
With a waterfall methodology, development begins after business requirements have been defined and a specification of requirements produced.
Governance and accountability flow from the specification of requirements and can be clearly defined contractually. DWP is familiar with this method of acquiring systems and managing projects.
However, in the case of UC, there is insufficient time to use a waterfall development methodology if the project deadline is to be met.
In addition, concerns raised that a waterfall methodology may not guarantee a new service that meets user requirements or may wrongly specify those requirements as the UC concept is so new and complex.
There is no guarantee of successful implementation at the end of the development process.
Agile
With an agile development methodology, requirements and code emerge through developers and users working together to define user stories that are then used to define processes .
A specification of requirements is not produced before starting programming thus saving time and effort.
Extensive use is made of prototyping.
The system is developed in small, iterative steps lasting up to two weeks. It is envisaged that this method will be able to deliver the core of UC before the go-live date as no time is wasted on writing a detailed systems specification.
A high level of rework is envisaged as business requirements are not clearly defined at the outset of the UC development.
Concerns are raised that Agile may not be able to address complex legacy systems integration.
Contracts for agile development are in their infancy. The DWP commercial team struggled to implement commercial terms for agile development that gave them control over the suppliers.
There is no guarantee of successful implementation at the end of the development process.

## Slide 17: Programme Reality

## Slide 18: Planned versus Actual Delivery, Sep 2013
 | 2011 plan | 2012 plan | 2013 actual
Job seekers allowance | inc | inc | Inc
Employment support allowance | Inc | Excl | Excl
Income support | Inc | Excl | Excl
Housing benefit | Inc | Excl | Excl
Working tax credits | Inc | Excl | Excl
Child tax credit | Inc | Excl | Excl
Difficult cases (eg couples) | Inc | Excl | Excl
Change of circumstances | Online | Phone | F2F
Automated IT systems |  |  | 
Online data capture for new claims | Yes | Yes | Yes
Calculation of gross income | Yes | Manual | Manual
Calculation of net income | Manual | Manual | Manual
Back office integration | Yes | Yes | Manual
Payments | Yes | Yes | Yes

## Slide 19: Planned take up rates versus actual rates
Between April 2013 and 31 October 2013, a total of 2,960 people started on Universal Credit
The majority are male, with a male to female ratio around 7:3
Most new claims are from unemployed people aged under 25
The Universal Credit caseload at 31 October 2013 was 2,720 and nearly 7 in 10 were under 25.
Source DWP analysis of Pathfinder statistics Oct 2013
Pathfinder statistics up to Oct 2013:

## Slide 20: Where did Universal Credit fail?
Policy clarity
Requirements clarity
Leadership
Vision
Commitment
Culture
Communications
Stakeholder engagement
Ensuring stakeholder support
Clear delivery plans
Risk management
Programme
assurance
management
& control
Procurement
Financial management
Universal Credit
Claimant journey
Access to systems
Migration plans
Staff training
Management information
Premises alterations
IT infrastructure
Identity assurance
Secure
processes
Systems integration
Legacy systems
integration

## Slide 21: Why did these failures occur?
Universal Credit
Political ambition versus programme reality
Failure to appreciate importance of IDA
Some claimants cannot adopt Digital by Default
Optimism bias
Is there such a thing as agile procurement?
No overarching programme design
Unfamiliar development methodology
Inconsistent leadership
Unrealistic delivery timetable
Failure to manage suppliers because of unfamiliar routes to procurement
Culture of distrust
Lack of clarity of requirements
Failure to heed warnings and advice
Too risky?
Domain knowledge
Failure to understand programme complexity
Failure to ask the right questions?
Correct policy assumptions?
Focus on technology rather than people

## Slide 22: Universal Credit: Where are we Now?

## Slide 23: 2014: A New Programme Approach
Twin track “Test and Learn” approach adopted:
  Development and delivery of an online digital service providing the full scope of Universal Credit;
  Expansion of the current ‘live service’ across North West England
Programme delivery timetable slipped to the right by 6 years: Rollout complete 2021?
Increased sustained rate of claimant on-boarding
Integration of the two systems not fully defined.
 | Comparison of Business Cases |  | 
 | 2012 | 2014 | 2016
DWP estimate of net benefit from UC | £38 billion | £21 billion | 
Number of claimants at Oct 2014 | 1.5 million | 17,850 (actual) | 60,000
DWP estimate of UC claimants by April 2016 | 5.5 million | 500,000 | 200,000
DWP estimate of UC claimants by 2017 | 8.2 million | - | -
DWP estimate of UC claimants by 2019 | - | 7 million | ?

## Slide 24: 2014: Impact on Rollout Plans

## Slide 25: 2016: House of Commons; Committee of Public Accounts
Most recent review: Universal Credit: progress update, 25th January 2016.
Key findings taken from the report:
  Universal Credit has stabilised, however, there remains a long way to go.
  Implementation has focussed mainly on the simplest cases
  DWP has again delayed the programme.
  The business case is out of date and does not reflect the changes to the tax and benefits system announced by George Osbourne in November 2015.
  The Office for Budget Responsibility forecasts that there will be a further six-month delay beyond the Department’s latest planned end-date.
And finally, the committee :
  “Remains disappointed by the persistent lack of clarity and evasive responses by the Department to our inquiries, particularly about the extent and impact of delays.”
  “The Department’s response to the previous Committee’s recommendations do not convince us that it is committed to improving transparency about the programme’s progress.”

## Slide 26: The Elephants Still in the Room……
Some claimants cannot adopt Digital by Default
Optimism bias
No up to date business case
Programme design still unclear
Unrealistic delivery timetable
Integration of the twin track approach unclear
Culture of distrust
Universal Credit
Benefits realisation unclear
No transitional strategy for claimants
Lack of transparency
Programme milestones still unclear

## Slide 27: Questions?